## Summary
Feature | Priority | Status | Owner | Time period | Notes
FP1: Produces power | Prio 3 | Not started
FP2: is certified | Prio 2 | Not started
FC1: Floats on water | Prio 1 | Not started
FC2: Is water tight | Prio 2 | Not started
FC3: Mechanically attached | Prio 1 | Not started
FC4: Does not go submarining under stream exposure, 3 m/s | Prio 3 | Not started
FC5: Feasible to change panel type, i.e from Chinese to US | Prio 2 | Not started
FC6: Resists high wind | Prio 3 | Not started
FC7: Resists waves up to 1.5 Hs | Prio 3 | Not started
FC8: Cheap to produce, cheaper total cost to install than competitors | Prio 1 | Not started
FC9: Grounding of the FPV unit | Prio 2 | Not started
FS1: Can walk on it | Prio 2 | Not started
FS2: Fast to produce, not necessarily mass producible | Prio 2 | Not started
FS3: Fast to install | Prio 3 | Not started

## Function - criteria - Solution
Column 1 | Names | Functions | Prio | Criteria | Solutions | Comment
FP1 | Power production | Produces power | 3 | Performance ratio (how much kWh per kWp), power density (kWp/sqm), soiling degree, cooling effect | PV panel
FP2 | Certification | is certified | 2 | Certification not broken by modification/assembly | Supplied certified | Check certification void conditions
FC1 | Buoyancy | Floats on water | 1 | Sufficient Buoyancy of the float / panel / hinges
FC2 | Water protection | Is water tight | 2 | Float must be water tight. minimize the degradation ratio and fault probability PV & electronics must be protected
FC3 | Mechnical performance | Mechanically attached | 1 | Tensile strength, shear strength, compression strength, fatigue strength safety value pass. is about the interconnection between floats
FC4 | Submarining | Does not go submarining under stream exposure, 3 m/s | 3 | resist 3m/s stream | Outsource the study
FC5 | Interchageability | Feasible to change panel type, i.e from Chinese to US | 2 | Keep design open to different standard size
FC6 | Wind resistance | Resists high wind | 3 | we keep the profile low and no wind traps
FC7 | Wave resistance | Resists waves up to 1.5 Hs | 3 | linked to the hinges and the strucutral integrity of the float |  | Long term goal
FC8 | Cost efficiency | Cheap to produce, cheaper total cost to install than competitors | 1 | As cheap or cheaper than competitors CAPEX wise (now 250€/kWp)
FC9 | Grounding system | Grounding of the FPV unit | 2 | maintainable grouding system of the floating matrix
FC10 | PV attachment | The PV needs to stick to the float | 1 | Must remained attached to the float, must allow for hinge to be attached to the FPV
FC11 | Mooring | Should be moored safely | 3
FC12 | Internal pressure control | Internal pressure control | 3 | No buldging, continious bonding of components
FS1 | Walkability | Can walk on it | 2 | Avoid microcrack when walking on it and float matrix must be stable
FS2 | Manufacturability | Fast to produce, not necessarily mass producible | 2 | Must be possible to assemble in Askim and should be exportable to the US. Objective: 90 to 900 floats per weeks for 2 people
FS3 | Deployability | Fast to install | 3 | plug and play electrically, objective: 20 kW installed per Man/hour, light FPV carried by 2 ppl, no tools

## Roadmap
REF NUMBER | Priority | Function | Task | Duration (person-weeks) | Start Week | End Week | Task owner | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
FC1 | 1 | Buoyancy | Single unit buoyancy | 4 | 1 | 4 | Team A | bar: 1 to 4
FC1 | 1 | Buoyancy | Float | 4 | 3 | 6 | Team A | bar: 3 to 6
FC1 | 1 | Buoyancy | Floating hinge | 3 | 5 | 7 | Team A | bar: 5 to 7
FC1 | 1 | Buoyancy | Using the PV+frame as a float | 3 | 6 | 8 | Team A | bar: 6 to 8
FC1 | 1 | Buoyancy | 1 hydroformed trough, 2 HF troughs, with different infills | 3 | 7 | 9 | Team A | bar: 7 to 9
FC1 | 1 | Buoyancy | Multiple unit buoyancy | 3 | 8 | 10 | Team A | bar: 8 to 10
FC1 | 1 | Buoyancy | Structural integrity of the assembled matrix | 2 | 10 | 11 | Team A | bar: 10 to 11
FC1 | 1 | Buoyancy | Fender on the matrix edge | 1 | 11 | 12 | Team A | bar: 11 to 12
FC3 | 1 | Mechanical performance | Sketch | 4 | 1 | 4 | Team B | bar: 1 to 4
FC3 | 1 | Mechanical performance | 3D design | 4 | 3 | 6 | Team B | bar: 3 to 6
FC3 | 1 | Mechanical performance | LS dyna simulation | 5 | 5 | 9 | Team B | bar: 5 to 9
FC3 | 1 | Mechanical performance | Optimize parameters | 4 | 8 | 11 | Team B | bar: 8 to 11
FC3 | 1 | Mechanical performance | Model scale test | 3 | 10 | 12 | Team B | bar: 10 to 12
FC3 | 1 | Mechanical performance | Fatigue | 3 | 11 | 13 | Team B | bar: 11 to 13
FC3 | 1 | Mechanical performance | Tensile strength | 2 | 12 | 13 | Team B | bar: 12 to 13
FC3 | 1 | Mechanical performance | Shear strength | 2 | 13 | 14 | Team B | bar: 13 to 14
FC3 | 1 | Mechanical performance | Compression strength | 2 | 14 | 15 | Team B | bar: 14 to 15
FC3 | 1 | Mechanical performance | Full scale prototype testing | 4 | 15 | 18 | Team B | bar: 15 to 18
FC3 | 1 | Mechanical performance | Source a new hinge | 1 | 18 | 18 | Team B | bar: 18
FC10 | 1 | PV attachment | Investigate glue | 4 | 1 | 4 | Team C | bar: 1 to 4
FC10 | 1 | PV attachment | Investigate weld | 4 | 4 | 7 | Team C | bar: 4 to 7
FC10 | 1 | PV attachment | Investigate roller hemming/seaming | 4 | 7 | 10 | Team C | bar: 7 to 10
FC10 | 1 | PV attachment | Investigate clinching | 4 | 10 | 13 | Team C | bar: 10 to 13
FC10 | 1 | PV attachment | Investigate bolting | 4 | 13 | 16 | Team C | bar: 13 to 16
FC10 | 1 | PV attachment | Final adjustments and review | 4 | 16 | 19 | Team C | bar: 16 to 19
FC2 | 2 | Water protection | Marine PU foam inside the float itself | 3 | 16 | 18 | Team A | bar: 16 to 18
FC2 | 2 | Water protection | Heighten the PV above the waterline | 3 | 18 | 20 | Team A | bar: 18 to 20
FC2 | 2 | Water protection | Protect the backside of the PV and the junction box with Foam | 2 | 20 | 21 | Team A | bar: 20 to 21
FC2 | 2 | Water protection | Extra protecting box with PM | 2 | 21 | 22 | Team A | bar: 21 to 22
FC2 | 2 | Water protection | Enhance the protection of the PV edge | 2 | 22 | 23 | Team A | bar: 22 to 23
FC2 | 2 | Water protection | Protect the cables going in and out of the float | 2 | 23 | 24 | Team A | bar: 23 to 24
FC2 | 2 | Water protection | MC4 connectors must be protected | 3 | 24 | 26 | Team A | bar: 24 to 26
FS1 | 2 | Walkability | Choose a glass/glass PV | 1 | 13 | 13 | Team A | bar: 13
FS1 | 2 | Walkability | Ensure the PV is supported on its backside | 2 | 13 | 14 | Team A | bar: 13 to 14
FS1 | 2 | Walkability | Study/test the buoyancy balance of a float | 2 | 14 | 15 | Team A | bar: 14 to 15
FP2 | 2 | Certification | Clear out with supplier what is possible to touch before breaking certification | 1 | 20 | 20 | Team C | bar: 20
FP2 | 2 | Certification | Supply a PV panel that is certified | 2 | 20 | 21 | Team C | bar: 20 to 21
FP2 | 2 | Certification | Investigate the certification specification (IEC, and UL) | 2 | 21 | 22 | Team C | bar: 21 to 22
FC5 | 2 | Interchangeability | Every 3D design should be done with regards to standard size | 1 | 19 | 19 | Team B | bar: 19
FC5 | 2 | Interchangeability | Assess the PV on the market (EU, CN, and US) | 2 | 19 | 20 | Team B | bar: 19 to 20
FC5 | 2 | Interchangeability | Find a common denominator to work with | 2 | 20 | 21 | Team B | bar: 20 to 21
FP1 | 3 | Power production | Sourcing a high kW output PV panel | 2 | 23 | 24 | Team C | bar: 23 to 24
FP1 | 3 | Power production | Sourcing a glass/glass PV panel for easy cleaning | 2 | 24 | 25 | Team C | bar: 24 to 25
FP1 | 3 | Power production | Sourcing a PV panel with a high-quality level | 2 | 25 | 26 | Team C | bar: 25 to 26
FP1 | 3 | Power production | Decide on an angle towards the sun | 2 | 26 | 27 | Team C | bar: 26 to 27
FC4 | 3 | Submarining | Design a stream-breaking bow potentially buoyant | 2 | 22 | 23 | Team B | bar: 22 to 23
FC4 | 3 | Submarining | Simulate | 2 | 23 | 24 | Team B | bar: 23 to 24
FC4 | 3 | Submarining | Parameter optimization | 2 | 24 | 25 | Team B | bar: 24 to 25
FC4 | 3 | Submarining | Scale model test | 2 | 25 | 26 | Team B | bar: 25 to 26

## Design
This page describe various aspects of the solution that touches one or more functions of the system
Each aspect can have multiple options that should be investigated.
Each combination of options for each aspect may be an eligible solution and should be assessed.
Frame / float relation | Float | Sheet shape | Dimples joining | Infill | Infill around junction box | Infill or frame air pockets | Attachment point to mooring system
1 Frame integrated float | 1 Single alu sheet | None | Glue | 1 Polystyrene | Infill split in to with gap | PU foam | 3 Half hinge
2 Separate frame and float | 2 Double alu sheet | 1 Through | Friction stir welding | Honeycomb | 1 Infill exact cutout | Potting | Full hinge
| Plastic | Through and dimples | Capacitance discharge welding | 1 Air | 2 None | 3 Air | intermediate float
|  | 1 Dimples | 3 None | 1 PU foam |  | Glue | inflatable buoy thing
Panel underside joining | Panel tilt | MC4 cables | Hinge / frame relation | Hinge reinforcement |  | Hinge edge coverage | Hinge material
1 Glue | 3 Slight tilt | 1 Through frame | Wrap around sheet edge | 2 None |  | 1 Along full edge of float | 3 PU
Heatable laminate | Flat | 2 Under frame | 1 Wrap around panel frame | 1 PVC pipe |  | Along partial edge of float | PP rope
2 None |  | Junction box on top | 2 Brackets joined to float | Corner hinge |  | 2 Individual hinges
|  |  | Brackets joined to panel frame | 1 Rope
Hinge buoyancy | Grounding type | Grounding cabling | Stream protection type | Stream protection fastening | Matrix edge protection | Dummy float | Water drainage
None | 3 Frame connected | 3 Alongside MC4s | Cylindrical width wise buoy | 1 Via hinge system | 1 Dummy float | Plastic | Plastic clip
1 Some | To water | Separate path | Cylindrical length wise buoy | To the float | 1 Cylindrical | 3 Same as float but with alu treadplates | 3 Metal clip
|  | None | 3 Bow shaped buoy | To the frame | 1 Same as stream protection |  | None
|  |  | Bow shape, non buoyant | 1 None (part of mooring) | 1 Barge
None
Stacking | Deployment | Hinge UV protection | Float extends panel area
Unassembled PV | Accordion | Sock around the hinge | 2 Yes
1 Vertical | 3 One by one | 3 Built into material | 1 No
1 Horizontal | 2 row by row
tilted
2 stories

## Design considerations
Double float, no dimples, through, slight tilt, infill, float extends panel area
Pros | Cons
Better hydrodynamic | more expensive
Better electrical protection, less splash | possibly more steps
Better against freezing water | lesser energy density
More robust | higher energy footprint
Easier to exchange solar panels | heavier - problem in production
Less complex due to separable components | heavier - installation/deployement
Facilitates edge clamps or alu lift profiles | Volumous shipping
Easier to make a water and air-tight construction, ex FSW first then inflate | Worse heat conductivity
More design freedom to shape and reshape
More space on the float
Higher buoyancy
Single float, dimples, no through, slight tilt, no infill, float does not extend
Pros | Cons
Very little material usage | Hetreogenous heat conduction (?)
Lightweight- better for production | Harder to protect against electrical faults
lightweight - installation/deployment | Less robust
More heat conductive | Less buoyancy
Price | Less options for changing panel in the field
Less volumous shipping | Worse regarding warranty
Enables bespoke frame/hinge integration
Hinge attached to float, single hinge, brackety, no reinforcement, PU
Pros | Cons
Based on current experience and work | Single point of force distribution
Simple hinge - no reinforcement | Many different components - stuff lost at site, stuff that can break, logistics, production time
Flexibility, can change hinges easily | Might allow whipping actions
Low UV exposure | More challenging to withstand compression
Cheap (casting, metal brackets) | Fastened on a thin part of the floating unit rather than a thick part
Brackets enable force distribution on the float
Many or few - flexible
Can avoid force on the float
Hinge attached to panel, full side of float hinge, no brackets, reinforced, PU
Pros | Cons
Homogenous distribution of force | Challenging tooling x2
Disallows splashing | Force goes directly into the panel
Offers buoyancy | Does not handle twisting well
Prevents compression effectively | Impossible to change a float or PV
Skip fastening of alu sheet to panel frame (potentially) | Worse regarding warranty
Protects from water intgress via the MC4 cable

## Design Per
Frame / float relation | Float | Sheet shape | Dimples joining | Infill | Infill around junction box | Infill or frame air pockets | Attachment point to mooring system
Half hinge
Separate frame and float | Double alu sheet | Through
Air
|  |  | None | PU foam
Panel underside joining | Panel tilt | MC4 cables | Hinge / frame relation | Hinge reinforcement | Roped hinges | Hinge edge coverage | Hinge material
| Slight tilt |  | Wrap around sheet edge | None | Rope |  | PU
|  | Under frame |  |  | No rope |  | PP rope
None | [5 empty] | Individual hinges
|  |  | Brackets joined to frame | Rope
Hinge buoyancy | Grounding type | Grounding cabling | Stream protection type | Stream protection fastening | Matrix edge protection | Dummy float | Water drainage
None | Frame connected | Alongside MC4s | Cylindrical buoy | Via hinge system | Dummy float |  | Plastic clip
|  |  | Bow shaped buoy | To the float | Cylindrical | Same as float but with alu treadplates | Metal clip
|  |  | Bow shape, non buoyant | To the frame | Same as stream protection |  | None
|  |  | None | None (part of mooring) | Barge
Stacking | Deployment | Hinge UV protection
Sock around the hinge
| One by one | Built into material
Horizontal | Same as rest of FPV
2 stories

## Design Guillaume
Replace with : edge joining = clinch
Frame / float relation | Float | Sheet shape | Dimples joining | Infill | Infill around junction box | Infill or frame air pockets | Attachment point to mooring system
|  |  | Glue | Polystyrene |  |  | Half hinge
Separate frame and float | Double alu sheet | Through | Friction stir welding |  | Infill exact cutout
| Plastic |  | Capacitance discharge welding |  |  | Air
Panel underside joining | Panel tilt | MC4 cables | Hinge / frame relation | Hinge reinforcement |  | Hinge edge coverage | Hinge material
| Slight tilt |  |  | None |  |  | PU
None |  | Junction box on top | Brackets joined to float |  |  | Individual hinges
Hinge buoyancy | Grounding type | Grounding cabling | Stream protection type | Stream protection fastening | Matrix edge protection | Dummy float | Water drainage
None | Frame connected | Alongside MC4s |  | Via hinge system | Dummy float
|  |  | Bow shaped buoy |  |  | Same as float but with alu treadplates | Metal clip
None (part of mooring)
Stacking | Deployment | Hinge UV protection
| One by one | Built into material
Horizontal

## Design - Eirik
Frame / float relation | Float | Sheet shape | Dimples joining | Infill | Infill around junction box | Infill or frame air pockets | Attachment point to mooring system
Frame integrated float | Single alu sheet |  |  |  |  | PU foam | Half hinge
|  |  |  | Air | None
|  | Dimples | None
Panel underside joining | Panel tilt | MC4 cables | Hinge / frame relation | Hinge reinforcement | Roped hinges | Hinge edge coverage | Hinge material
Glue | Slight tilt | Through frame |  |  | Rope | Along full edge of float | PU
|  |  | Wrap around panel frame | PVC pipe
Rope
Hinge buoyancy | Grounding type | Grounding cabling | Stream protection type | Stream protection fastening | Matrix edge protection | Dummy float | Water drainage
| Frame connected | Alongside MC4s |  | Via hinge system
Some |  |  | Bow shaped buoy |  |  | Same as float but with alu treadplates | Metal clip
Same as stream protection
Stacking | Deployment | Hinge UV protection
Vertical | One by one | Built into material
Same as rest of FPV

## Tasks
Create LS Dyna simulations for hinge. Must be able to take a parameterized cad model (freecad is best) and create a set of output parameters and a score from 0 to 1.
Calculate hinge with octopatch for Surewave
Calculate hinge with oring design
Create fatigue tests for any hinge. LS Dyna? Another tool? IFE?
Create hinge sample for physical testing by Sintef in chinese material
Create miniature of current octopatch design for wave tank testing
Test fluid forming pressing DIY like punch die
Fluid forming pressing DIY from tip
Double sheet fluid forming pressing DIY
Test buoyancy of miniature octopatch with float
Decide on how to get cable through frame in a water-tight manner
Get quotes for honeycomb and polystyrene
Research PU Foam and test design tests for water integrity
Research need for "mattress" under glass glass solar panel on different underlying solutions (honeycomb, cups, pu foam, polystyrene, alu sheet)
Research connection method for flat aluminum om alu frame

## FP1
Function | Criteria | HOW
Produces power | Performance ratio (how much kWh per kWp), power density (kWp/sqm), soiling degree, cooling effect | Sourcing a high kW output PV panel
Sourcing a glass/glass PV panel for easy cleaning
Sourcing a PV panel with high quality level
Decide of an angle towards the sun

## FP2
Function | Criteria | How
Certiication | Certification not broken by modification/assembly | Clear out with supplier what is posible to touch before breaking certification
Supply a PV panel that is certified
Investagate the certification specification (IEC, and UL) to see if there are voiding conditions

## FC1
Function | Criteria | How
Floats on water | Sufficient Buoyancy of the float / panel / hinges | Single unit buoyancy
Float
floating hinge
Using the PV+frame as a float
1 hydroformed trofe, 2 HF trofes, with different infils,
Multiple unit buoyancy
Strucutral integraity of the assembled matrix
Saussage on the matrix edge

## FC2
Function | Criteria | How
Is water tight | Float must be water tight. minimize the degradation ratio and fault probability PV & electronics must be protected | Marine PU foam inside the float it self
Heighten the PV above the water line
Protect the backside of the PV and the junction box with Foam
Extra protecting box with PM
Enhance the protection of the PV edge
Protect the Cables going in and out of the float
MC4 connectors must be protected

## FC3
Function | Criteria | How
Is mechanically attached | Tensile strength, shear strength, compression strength, fatigue strength safety value pass. | Sketch
3D design
LS dyna simu
optimze parameters
Model scale test
Fatigue
|  | Tensile str | Lab testing by SINTEF
Shear str
compression str
Full scale prototype testing
Source a new hinge

## FC4
Function | Criteria | How
Submarining | resist 3m/s stream | Design a stream breaking bow potentially buoyant
Simulate "
Parameter optimization
Scale model test
Source a product out of the shelve

## FC5
Function | Criteria | How
Interchangeability | Keep design open to different standard size | Every 3D design should be done with regards to standard size
Assess the PV on the market (EU, CN and US)
Find a common denominator to work with

## FC6
Function | Criteria | How / Sub fonction
Resists high wind | profile low and no wind traps | Avoid lift
Safety factor for wind induced load
CFD wind software

## FC7
Function | Criteria | How
Resists waves | linked to the hinges and the strucutral integrity of the float | Work with MARIN (From Surewave) to evaluate the new loads on a matrix of different sizes
| safety factor for the hinge performances | Apply those loads to a simulation and check that our hinge system validates the safety factor
| Resist wave up to 1.5 Hs | Possibly an external consultancy

## FC8
Function | Criteria | How
Cost efficiency | As cheap or cheaper than competitors CAPEX wise (now 250€/kWp) | Cheap PV compared to kWp output
Cheap float
Simplest assembly
Number of components should be low
Number of assembly steps should be low
Cost of extra component should be low
Keep frakt lowest
Cheap infrastructure for prod

## FC9
Function | Criteria | How
Grounding system | Must resist corrosion and constant movement (fatigue) | develop and reinforce the mainnheim system
Attachment
Guide over the FPV

## FC10
Function | Criteria | How
PV attachment | Ease of operation | Investigate glue
| Infrastrucutre costs | Investigate weld
| Components costs | Investigate roller hemming/seaming
| Durability | Investigate clinching
| water protection | Investigate bolting

## FC11
Function | Criteria | How
Mooring | System must remain in place safely | Design a mooring system for stream water
Design a mooring system for nearshore/offshore water
Design a mooring system for still water

## FC12
Function | Criteria | How
Internal pressure control | No overpressure | Exhaust hole in float
| No cavity | QA on production

## FS1
Function | Criteria | How
Can walk on it | Avoid microcrack when walking on it and float matrix must be stable | Chose a glass/glass PV
Ensure the PV is supported on its backside
Study/test the buoyancy balance of a float

## FS2
Function | Criteria | How / Sub fonction
Manufacturability | Must be possible to assemble in Askim | Processes compatible with mass production
| should be exportable to the US. Objective: 90 to 900 floats per weeks for 2 people | Processes compatible with organic production

## FS3
Function | Criteria | How
Fast to install | Plug and play electrically, | Use standard connectors
| Objective: 20 kW installed per Man/hour, | Ensure ease of handling
| Light FPV carried by 2 ppl | Ensure personnel safety
| No tools | Ensure equipment safety

## Roadmap_old
Product v2 development timeline
PROJECT TITLE |  |  |  |  | Product B development | COMPANY NAME |  | Sunlit Sea
PROJECT MANAGER |  |  |  |  | Eirik Larsen | DATE |  | 2024-08-29
[6 empty] | PHASE ONE: Conception |  |  |  | PHASE TWO: Simulation |  |  | PHASE THREE: Prototyping |  |  | PHASE FOUR: Final test
[6 empty] | WEEK 1 | WEEK 2 |  | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
REF NUMBER | Priority | Function | Task | Duration (person-weeks) | TASK OWNER
FP1 | 3 | Power production |  | 4
Sourcing a high kW output PV panel
Sourcing a glass/glass PV panel for easy cleaning
Sourcing a PV panel with high quality level
Decide of an angle towards the sun
FP2 | 2 | Certification |  | 1
Clear out with supplier what is posible to touch before breaking certification
Supply a PV panel that is certified
Investagate the certification specification (IEC, and UL) to see if there are voiding conditions
FC1 | 1 | Buoyancy |  | 12
Single unit buoyancy
Float
floating hinge
Using the PV+frame as a float
1 hydroformed trofe, 2 HF trofes, with different infils,
Multiple unit buoyancy
Strucutral integraity of the assembled matrix
Saussage on the matrix edge
FC2 | 2 | Water protection |  | 12
Marine PU foam inside the float it self
Heighten the PV above the water line
Protect the backside of the PV and the junction box with Foam
Extra protecting box with PM
Enhance the protection of the PV edge
Protect the Cables going in and out of the float
MC4 connectors must be protected
FC3 | 1 | Mechnical performance |  | 20
Sketch
3D design
LS dyna simu
optimze parameters
Model scale test
Fatigue
Tensile str
Shear str
compression str
Full scale prototype testing
Source a new hinge
FC4 | 3 | Submarining |  | 4
Design a stream breaking bow potentially buoyant
Simulate "
Parameter optimization
Scale model test
Source a product out of the shelve
FC5 | 2 | Interchageability |  | 1
Every 3D design should be done with regards to standard size
Assess the PV on the market (EU, CN and US)
Find a common denominator to work with
FC6 | 3 | Wind resistance |  | 1
Avoid lift
Safety factor for wind induced load
CFD wind software
FC7 | 3 | Wave resistance |  | 2
Work with MARIN (From Surewave) to evaluate the new loads on a matrix of different sizes
Apply those loads to a simulation and check that our hinge system validates the safety factor
Possibly an external consultancy
FC8 | 1 | Cost efficiency |  | 2
Cheap PV compared to kWp output
Cheap float
Simplest assembly
Number of components should be low
Number of assembly steps should be low
Cost of extra component should be low
Keep frakt lowest
Cheap infrastructure for prod
FC9 | 2 | Grounding system |  | 3
develop and reinforce the mainnheim system
Attachment
Guide over the FPV
FC10 | 1 | PV attachment |  | 5
Investigate glue
Investigate weld
Investigate roller hemming/seaming
Investigate clinching
Investigate bolting
FC11 | 3 | Mooring |  | 3
Design a mooring system for stream water
Design a mooring system for nearshore/offshore water
Design a mooring system for still water
FC12 | 3 | Internal pressure control |  | 1
Exhaust hole in float
QA on production
FS1 | 2 | Walkability |  | 3
Chose a glass/glass PV
Ensure the PV is supported on its backside
Study/test the buoyancy balance of a float
FS2 | 2 | Manufacturability |  | 3
Processes compatible with mass production
Processes compatible with organic production
FS3 | 3 | Deployability |  | 3
Use standard connectors
Ensure ease of handling
Ensure personnel safety
Ensure equipment safety